## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE 1 |  |  |  | PHASE 2 | [9 empty] | PHASE 3
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3
[7 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Milestone: Initial tasks
Create Project Main |  | 11/06/ | 11/06/ | 2hr | Marco | Done | bar: WEEK 1 M
Stakeholder Analysis |  | 11/07/ | 11/07/ | 2hr | Marco | Done | bar: WEEK 1 T
Project Plan |  | 11/08/ | 11/08/ | 2hr | Marco | Done | bar: WEEK 1 W
Search documentation |  | 11/09/ | 11/09/ | 2hr | Marco | Done | bar: WEEK 1 R
Milestone: Revenue and Profit
Revenue and profit: total sales. Matrix. Measure |  | 11/10/ | 11/10/ | 1hr | Marco | Done | bar: WEEK 1 F
Revenue and profit: total profit. Matrix. Measure |  | 11/10/ | 11/10/ | 1hr | Marco | Done | bar: WEEK 1 F
Revenue and profit: gross profit margin. Matrix. Measure |  | 11/11/ | 11/11/ | 1hr | Marco | Done | bar: WEEK 1 S
Revenue and profit:Total sales by unit of time. Cumulative chart | Cumulative and non cumulative bar chart | 11/11/ | 11/11/ | 1hr | Marco | Done | bar: WEEK 1 S
Revenue and profit: Total sales with filters. Bar chart |  | 11/12/ | 11/12/ | 1hr | Marco | Done | bar: WEEK 1 U
Revenue and profit: Total sales by territory, product, and customer. Table |  | 11/12/ | 11/12/ | 1hr | Marco | Done | bar: WEEK 1 U
Milestone: Sales Analysis and Additional Measures
Sales Analysis: Gross sales |  | 11/13/ | 11/13/ | 1hr | Marco | Done | bar: WEEK 2 M
Sales Analysis: Sales growth rate |  | 11/13/ | 11/13/ | 1hr | Marco | Done | bar: WEEK 2 M
Sales Analysis: Average transaction value |  | 11/14/ | 11/14/ | 1hr | Marco | bar: WEEK 2 T
Sales Analysis: Sales by product or category |  | 11/14/ | 11/14/ | 1hr | Marco | bar: WEEK 2 T
Sales Analysis: Sales by region, channel, or customer segment |  | 11/15/ | 11/15/ | 1hr | Marco | bar: WEEK 2 W
Operating income: Matrix. Measure |  | 11/15/ | 11/15/ | 1hr | Marco | bar: WEEK 2 W
Gross margin: Matrix. Measure. Comparison? |  | 11/16/ | 11/16/ | 2hr | Marco | bar: WEEK 2 R
Milestone: Income Statement
Income statement: Revenue. Unit of time. Bar chart |  | 11/17/ | 11/17/ | 2hr | Marco | bar: WEEK 2 F
Income statement: COGS |  | 11/18/ | 11/18/ | 1hr | Marco | bar: WEEK 2 S
Income statement: Gross profit |  | 11/18/ | 11/18/ | 1hr | Marco | bar: WEEK 2 S
Income statement: Operating expenses |  | 11/19/ | 11/19/ | 40min | Marco | bar: WEEK 2 U
Income statement: Operating income. Unit of time and segment. Table |  | 11/19/ | 11/19/ | 40min | Marco | bar: WEEK 2 U
Income statement: Net income |  | 11/19/ | 11/19/ | 40min | Marco | bar: WEEK 2 U
Milestone: Revue
Check dasboards |  | 11/20/ | 11/20/ | 2hr | Marco | bar: WEEK 3 M
Check Captain's log |  | 11/21/ | 11/21/ | 2hr | Marco | bar: WEEK 3 T
Final assessment |  | 11/22/ | 11/22/ | 2hr | Marco | bar: WEEK 3 W
Permanent Tasks
Captain's log. Fill the document with the formulas |  | 11/06/ | 11/21/ | 15min | Marco | bar: WEEK 1 M to WEEK 3 W
Check and complete documentation |  | 11/06/ | 11/21/ | 30min | Marco | bar: WEEK 1 M to WEEK 3 W

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Revenue and profit: total sales. Matrix. Measure | Done
Revenue and profit: total profit. Matrix. Measure | Done
Revenue and profit: total margins. Matrix. Measure
Revenue and profit:Total sales by unit of time. Cumulative chart
Revenue and profit: Total sales with filters. Bar chart
Revenue and profit: Total sales by territory, product, and customer. Table
Sales Analysis: Gross sales
Sales Analysis: Sales growth rate
Sales Analysis: Average transaction value
Sales Analysis: Sales by product or category
Sales Analysis: Sales by region, channel, or customer segment
Operating income: Matrix. Measure
Gross margin: Matrix. Measure. Comparison?
Income statement: Revenue. Unit of time. Bar chart
Income statement: COGS
Income statement: Gross profit
Income statement: Operating expenses
Income statement: Operating income. Unit of time and segment. Table
Income statement: Net income

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5